# Project lifecycle at a glance

| Stage | Main question | Key output / evidence |
| --- | --- | --- |
| 1. Initiate | What problem are we solving, and for whom? | Approved project charter; target users and beneficiaries; project purpose; initial stakeholder list; success criteria and initial assumptions. |
| 2. Plan | What will the marketplace deliver, by when, and with what resources? | Approved management plan; scope and requirements baseline; WBS and schedule; budget and resource plan; risk register; quality, communication and change-control plans. |
| 3. Execute | How will the team create the planned marketplace outputs? | Approved seller, customer and admin journeys; responsive-web MVP implementation; product catalogue and order workflows; payment and delivery coordination; user and operations guides. |
| 4. Monitor & control | Are scope, schedule, budget, quality and risks on track? | Progress reports; schedule and budget variance tracking; updated risk, issue and change logs; requirement and test evidence; monitoring of pilot performance against agreed targets. |
| 5. Close | Have objectives and acceptance criteria been met, and what did we learn? | Accepted deliverables; eight-week pilot evaluation against agreed KPIs; handover and operating guidance; outstanding actions; lessons learned; formal closure approval. |

# 1. Project overview and charter

| Project title | Women Home-Based Business Marketplace (WHBBM) |
| --- | --- |
| Problem / opportunity | Women running home-based businesses often sell through separate social-media pages and messaging apps, making product discovery, order tracking, payment coordination and delivery updates difficult to manage consistently. |
| Target users / beneficiaries | Primary: women running home-based businesses. Secondary: customers seeking home-produced goods, crafts, accessories, clothing and gifts. Operational: platform administrators, payment providers and delivery partners. |
| Project purpose | Plan, design, develop, test and pilot a central marketplace that helps women-owned home businesses present products, manage orders and coordinate payment and delivery, while providing customers with a clear purchase journey. |
| SMART objective | Within 16 weeks of project approval, deliver a responsive-web MVP with seller onboarding, product listings, customer browsing and ordering, order-status tracking, admin moderation and payment/delivery coordination; then complete an 8-week pilot with at least 15 active sellers, 75 approved listings, 70% order fulfilment among seller-accepted orders, and average customer satisfaction of at least 4/5 from 20 or more responses. |
| Proposed solution | A mobile-friendly multi-seller web marketplace with seller profiles, product catalogue and availability; customer search, filtering and ordering; seller order management; order-status updates; cash-on-delivery and one third-party online payment option; delivery coordination; basic seller sales summaries; and an admin console for seller/listing review and complaint handling. |
| Expected benefits | Greater product visibility for home-based sellers; access to customers beyond personal networks; more organised product and order management; clearer payment and delivery information; and improved visibility of basic sales and order performance. |
| Success criteria | MVP ready within 16 weeks; at least 15 active sellers and 75 approved listings at pilot start; at least 70% fulfilment of seller-accepted orders during the 8-week pilot; average satisfaction of at least 4/5 from a minimum of 20 customer responses; no open critical-severity defects at pilot launch. |
| Constraints / assumptions | Initial release is a responsive website, not native mobile apps. Pilot launch is limited to one selected geographic area and crafts, accessories, clothing and gifts. Checkout is limited to one seller per order. Payment and delivery services use external providers. Sellers and customers have internet access and smartphones. Budget, launch area and service providers are confirmed during initiation. |

## SMART objective check

| Specific | Measurable | Achievable | Relevant | Time-bound |
| --- | --- | --- | --- | --- |
| Deliver and pilot a responsive-web marketplace MVP. | 15 active sellers; 75 listings; 70% order fulfilment; satisfaction ≥4/5 from 20+ responses. | Focus on essential marketplace functions and external payment/delivery providers. | Improves sales access and order management for women-led home businesses. | MVP in 16 weeks; pilot completed by Week 24 after approval. |

# 2. Scope and requirements management

| In scope | Out of scope |
| --- | --- |
| Responsive web marketplace; seller registration/profile and product listing; product categories, images, price and availability; customer browse/search/filter; order checkout for one seller; seller order management and status tracking. | Native iOS/Android applications; multi-seller cart or single checkout across multiple sellers; international launch; own delivery fleet, warehouse or fulfilment centres. |
| Admin console for seller/listing review and complaints; cash-on-delivery and one third-party online payment option; external delivery coordination; basic seller sales/order summaries; privacy, access control and security; testing, pilot and handover. | AI product recommendations; loyalty points; seller loans/financing; advanced marketing automation; paid seller subscriptions; products outside the approved launch categories. |

## Requirements list

| ID | Requirement / need | Priority | How to verify | Owner |
| --- | --- | --- | --- | --- |
| REQ-01 | Sellers can register, create a profile and submit products with name, category, description, price, images and availability; new listings require admin approval. | H | Seller onboarding and listing acceptance tests; verify required fields and approval flow. | Product Owner / Business Analyst |
| REQ-02 | Customers can browse approved products, search and filter by category, and view product and seller details. | H | Customer journey tests for search, filters, product detail and seller information. | UX/UI Lead |
| REQ-03 | Customers can place an order for products from one seller, enter delivery details, review item price and delivery fee, and receive an order reference. | H | End-to-end checkout tests, including invalid or missing order information. | Product Owner / Business Analyst |
| REQ-04 | Sellers can accept or reject orders and update preparation status; customers can view the latest order status. | H | Order workflow tests for acceptance, rejection, cancellation, dispatch and completion. | Development Lead |
| REQ-05 | The marketplace supports cash-on-delivery and one approved third-party online payment option, recording payment status for each order. | H | Payment scenario tests for success, failure, cancellation and cash collection. | Payments / Operations Lead |
| REQ-06 | The marketplace records delivery address, fee, delivery partner/reference and delivery status; initial coordination may be manual or partner-based. | H | Delivery workflow review covering assignment, tracking, failed delivery and completion. | Operations Lead |
| REQ-07 | Administrators can review and remove listings, manage seller accounts, and log and track customer complaints. | H | Admin acceptance tests for approval, removal, account suspension and complaint handling. | Platform Admin / Product Owner |
| REQ-08 | Sellers can view basic order and sales summaries; access is role-based, customer data is protected, and key journeys are mobile-friendly. | M | Dashboard review plus access-control, privacy/security checklist and mobile-device tests. | Development Lead / QA Lead |

# 3. Deliverables and acceptance criteria

| Deliverable ID / name | Owner | Due date | Acceptance criteria / evidence | Approver |
| --- | --- | --- | --- | --- |
| D1: Business requirements and scope baseline | Product Owner / Business Analyst | Week 2 | Approved problem statement, target users, product scope, prioritised requirements, assumptions, constraints and primary user journeys. | Project Sponsor / Project Manager |
| D2: UI/UX designs and clickable prototype | UX/UI Lead | Week 5 | Seller, customer and admin flows covered; responsive screen designs and clickable prototype reviewed; key feedback and approvals recorded. | Product Owner / Sponsor |
| D3: Responsive-web marketplace MVP | Technical / Development Lead | Week 14 | Prioritised MVP functions are available: seller onboarding and listings, customer discovery and ordering, seller order management, admin moderation, payment status and delivery coordination. | Project Sponsor / Product Owner |
| D4: QA, security and user-acceptance report | QA Lead | Week 16 | Functional, responsive, access-control and security checks completed; critical defects closed; user-acceptance results, defects and approvals recorded. | Project Sponsor / Product Owner |
| D5: Pilot launch and evaluation report | Operations Lead | Week 24 | Eight-week pilot results recorded against targets: 15 active sellers, 75 approved listings, 70% fulfilment of accepted orders and average satisfaction of 4/5 from at least 20 responses; improvement actions documented. | Project Sponsor |
| D6: Handover and operations pack | Project Manager / Operations Lead | Week 24 | User/admin guides, support and escalation process, payment/delivery coordination steps, data/privacy procedures, known limitations and outstanding actions are handed over. | Project Sponsor / Operations Owner |

# 4. Work breakdown structure (WBS)

| WBS code | Work package / task | Output | Responsible role | Timing |
| --- | --- | --- | --- | --- |
| 1.0 | Initiation and requirements baseline (D1) | Approved charter, problem statement, scope baseline, prioritised REQ-01 to REQ-08, assumptions, constraints and primary user journeys | Product Owner / BA, with Project Manager | Weeks 1–2 |
| 2.0 | UI/UX design and clickable prototype (D2) | Seller, customer and admin flows; responsive screen designs; clickable prototype with feedback and approval recorded | UX/UI Lead | Weeks 3–5 |
| 3.0 | Responsive-web MVP development (D3) | Working MVP covering the prioritised requirements, with release notes and test evidence | Development Lead | Weeks 6–14 |
| 3.1 | Seller onboarding and listings (REQ-01) | Seller registration, profile, product listing and admin approval flow | Development Lead | Weeks 6–14 |
| 3.2 | Customer browsing, search and ordering (REQ-02, REQ-03) | Browse, search, filter, product detail and single-seller checkout with order reference | Development Lead | Weeks 6–14 |
| 3.3 | Seller order management and status tracking (REQ-04) | Accept/reject orders, preparation status and customer-visible order status | Development Lead | Weeks 6–14 |
| 3.4 | Payment and delivery coordination (REQ-05, REQ-06) | Cash-on-delivery and one online payment option; delivery details, fee, reference and status | Payments / Operations Lead | Weeks 6–14 |
| 3.5 | Admin console, seller summaries and access control (REQ-07, REQ-08) | Listing moderation, account management, complaint log, basic sales summaries, role-based access | Development Lead | Weeks 6–14 |
| 4.0 | QA, security and user acceptance (D4) | Functional, responsive, access-control and security checks; critical defects closed; user-acceptance results and approvals | QA Lead | Weeks 15–16 |
| 5.0 | Pilot launch and evaluation (D5) | Eight-week pilot results against targets (15 sellers, 75 listings, 70% fulfilment, 4/5 satisfaction) and improvement actions | Operations Lead | Weeks 17–24 |
| 5.1 | Seller recruitment and onboarding | 15 active sellers and 75 approved listings ready at pilot start; Week 12 checkpoint | Operations Lead | Weeks 1–16 |
| 6.0 | Handover and operations pack (D6) | User/admin guides, support and escalation process, payment/delivery steps, data/privacy procedures, known limitations | Project Manager / Operations Lead | Week 24 |
| 7.0 | Project management and final documentation | Management plan, status reports, logs, change control, final report and presentation | Project Manager, with Documentation & Presentation Lead | Weeks 1–24 |

The WBS follows the deliverables D1 to D6 in section 3 and the 24-week plan used throughout this document.

# 5. Schedule and milestones

| Task / milestone | Depends on | Weeks | Start | Finish | Responsible role | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Management plan final submission (graduation project) | Plan sections complete | Before Week 1 | 2026-11-29 | 2026-12-02 | Documentation & Presentation Lead | Not started |
| Budget, launch area and service providers confirmed (I-01) | — | Weeks 1–2 | 2026-12-06 | 2026-12-19 | Project Manager / Project Sponsor | Not started |
| D1 Business requirements and scope baseline approved | I-01; charter | Weeks 1–2 | 2026-12-06 | 2026-12-19 | Product Owner / BA | Not started |
| Payment sandbox access (D-02) and delivery process (D-03) agreed | I-01 | Weeks 1–4 | 2026-12-06 | 2027-01-02 | Payments / Operations Lead; Operations Lead | Not started |
| D2 UI/UX designs and clickable prototype approved | D1 | Weeks 3–5 | 2026-12-20 | 2027-01-09 | UX/UI Lead | Not started |
| D3 Responsive-web MVP complete | D2 | Weeks 6–14 | 2027-01-10 | 2027-03-13 | Development Lead | Not started |
| Seller recruitment: 15 active sellers, 75 approved listings (checkpoint Week 12) | D1 | Weeks 1–16 | 2026-12-06 | 2027-03-27 | Operations Lead | Not started |
| D4 QA, security and user-acceptance report approved | D3 | Weeks 15–16 | 2027-03-14 | 2027-03-27 | QA Lead | Not started |
| D5 Pilot (8 weeks) and evaluation report | D4; recruitment | Weeks 17–24 | 2027-03-28 | 2027-05-22 | Operations Lead | Not started |
| D6 Handover and operations pack; project closure | D5 | Week 24 | 2027-05-16 | 2027-05-22 | Project Manager / Operations Lead | Not started |

The management plan is submitted on 2 December 2026. Week 1 of the project is assumed to start on Sunday 6 December 2026; indicative dates move if the start date moves. Planning documents stay v0.1 drafts until approved. Deliverable weeks match section 3.

# 6. Team structure and responsibilities

| Role | Main responsibilities | Role assignment / backup |
| --- | --- | --- |
| Project Manager / Team Lead | Coordinates plan, meetings, dependencies, reporting, and escalation. | Project Manager / Deputy Project Manager |
| Project Sponsor (Supervisor / Assessor) | Confirms budget, launch area and providers; approves deliverables D1–D6 and major changes. | Supervisor / Assessor |
| Product Owner / Business Analyst (Research & Requirements Lead) | Collects evidence, consults users, documents and prioritises requirements, and owns the scope baseline. | Product Owner / BA / Research Support |
| UX/UI Lead (UI/UX & Solution Design Lead) | Designs seller, customer and admin flows and the clickable prototype. | UX/UI Lead / another team member (backup owner, R7) |
| Development Lead (Delivery / Technical Lead) | Coordinates design, development, implementation, or process solution. | Development / Technical Lead / Technical Support |
| QA Lead (Quality & Testing Lead) | Defines checks, records defects, verifies criteria and evidence. | Quality Assurance (QA) Lead / QA Support |
| Operations Lead | Runs seller recruitment and onboarding, delivery coordination, the pilot, feedback and complaints. | Operations Lead / another team member (backup owner, R7) |
| Payments / Operations Lead | Manages the payment provider, sandbox access, payment status and delivery tests. | Payments / Operations Lead / another team member (backup owner, R7) |
| Documentation & Presentation Lead | Maintains version control, report structure, slides, and references. | Documentation & Presentation Lead / Documentation Support |

## Simple RACI matrix

| Activity | Project lead | Team member(s) | Supervisor / client |
| --- | --- | --- | --- |
| Approve scope | R | C | A |
| Conduct research | A/C | R | I/C |
| Approve major change | R | C | A |
| Verify deliverable | C | R | A/C |
| Accept final project | R | C | A |

R = Responsible, A = Accountable, C = Consulted, I = Informed. In this matrix Project lead = Project Manager, and Supervisor / client = Project Sponsor (the Supervisor / Assessor). Owner / responsible-role fields use job titles rather than individual names; one team member may hold more than one role, and members are assigned to roles separately.

# 7. Communication and meeting plan

Who needs which information, how often, through which channel, and who is responsible for sending it and keeping a record.

| Communication | Audience | Frequency / timing | Channel | Owner / record |
| --- | --- | --- | --- | --- |
| Team check-in | All team members | Weekly; twice weekly in Weeks 12–16 (MVP build and QA) | Meeting / chat | Project Manager; action log |
| Sponsor update | Project Sponsor + Product Owner | Every 2 weeks, or as agreed | Email + 30-minute meeting | Project Manager; status report |
| Milestone review | Team + Sponsor / Product Owner | At each milestone: D1 Week 2, D2 Week 5, D3 Week 14, D4 Week 16, D5 and D6 Week 24 | Review session | Deliverable owner; decision log |
| Provider coordination | Payments/Operations Lead + payment and delivery providers | Every 2 weeks during build; weekly during the pilot | Email / call | Payments/Operations Lead; dependency log |
| Pilot seller and customer feedback | Pilot sellers and customers | Weekly during the 8-week pilot (Weeks 17–24) | Messaging group / feedback form | Operations Lead; feedback and complaint log |
| Urgent escalation | Relevant owner + Project Manager (+ Sponsor if critical) | Within 24 hours of a critical blocker | Agreed channel (call / chat), then email confirmation | Person raising the issue; issue log |

## Meeting rules

- Share an agenda before each meeting; keep discussion focused on decisions, progress, blockers and next actions.

- Record decisions, action owner, due date and unresolved questions.

- If a member cannot attend, they send an update beforehand and review the notes afterwards.

- Escalate urgent risks or blockers promptly (for example a payment provider failure or a critical defect); do not wait for the next scheduled meeting.

# 8. Risk management

Probability and impact are scored from 1 (low) to 5 (high). Risk score = probability × impact. Risks scoring 12 or more need an active response.

| ID / risk | P (1–5) | I (1–5) | Score | Response / mitigation | Owner / trigger |
| --- | --- | --- | --- | --- | --- |
| R1: Scope expands (e.g. multi-seller cart, native apps, loyalty points) | 4 | 4 | 16 | Avoid: freeze the D1 scope baseline; use change control; deliver High-priority REQ-01 to REQ-07 first. | Product Owner / BA; any request outside the approved scope |
| R2: Too few sellers or listings recruited (target: 15 active sellers, 75 approved listings at pilot start) | 3 | 5 | 15 | Mitigate: start recruitment early through women's groups and local networks; offer onboarding and listing-creation support. | Operations Lead; recruitment below 50% of target by Week 12 |
| R3: Payment or delivery provider delay or integration problem | 3 | 4 | 12 | Mitigate / transfer: confirm providers during initiation; test in sandbox early; fall back to cash-on-delivery and manual delivery coordination. | Payments/Operations Lead; provider misses an agreed integration date |
| R4: Low order fulfilment or satisfaction in the pilot (target: 70% of seller-accepted orders, 4/5 average) | 3 | 4 | 12 | Mitigate: seller training, order reminders, fast complaint handling through the admin console. | Operations Lead; fulfilment below 70% for 2 consecutive weeks |
| R5: Critical defects remain at pilot launch | 3 | 4 | 12 | Mitigate: test during development; complete QA and user acceptance by Week 16; no go-live with open critical defects. | QA Lead; critical defect still open during Weeks 15–16 |
| R6: Customer data privacy or security incident | 2 | 5 | 10 | Mitigate: role-based access; collect minimum data; online payments handled by the third-party provider; security checklist in D4. | Development Lead; failed access-control or security check |
| R7: Team member delay | 3 | 3 | 9 | Mitigate: interim deadlines, knowledge sharing, and a backup owner for each deliverable. | Project Manager; missed checkpoint |
| R8: Budget, launch area or service providers not confirmed during initiation | 2 | 4 | 8 | Mitigate: confirm all three before D1 approval (Week 2); escalate to the Sponsor if still open. | Project Manager / Sponsor; still open at Week 2 |

Score key: 15–25 high (red); 10–14 medium (amber); below 10 low (green).

## Risk response options

- Avoid: change the plan to remove the threat (R1).

- Mitigate: reduce probability or impact (R2–R8).

- Transfer / share: allocate part of the impact to another party, such as the online payment provider (R3, R6).

- Accept: monitor the risk and prepare a contingency if needed.

- Exploit / enhance / share: for opportunities, e.g. partnering with a women's business group to speed up seller recruitment.

# 9. Issue, assumption, dependency, and decision logs

Logs capture information that can affect delivery: current problems, unverified beliefs, work that relies on something else, and decisions the team has made. Update this log throughout the project.

| ID / date | Item and impact | Owner | Next action / due date | Status |
| --- | --- | --- | --- | --- |
| I-01 / Week 1 | Issue: budget, launch area and service providers are not yet confirmed; this blocks D1 and provider selection. | Project Manager | Confirm with the Sponsor by Week 2 | Open |
| A-01 / Week 1 | Assumption: sellers and customers have internet access and smartphones; if not, a responsive website would reach fewer users. | Product Owner / BA | Validate with a short seller/customer survey by Week 2 | Open |
| A-02 / Week 1 | Assumption: one seller per order is sufficient for the pilot; if customers need multi-seller carts, scope would change. | Product Owner / BA | Validate through prototype feedback by Week 5 | Open |
| D-01 / Week 1 | Dependency: D3 MVP (Week 14) relies on D2 prototype approval (Week 5); late approval delays development. | UX/UI Lead | Obtain recorded approval at the Week 5 milestone review | Open |
| D-02 / Week 1 | Dependency: REQ-05 payment status relies on the third-party payment provider account and sandbox access. | Payments/Operations Lead | Request provider access by Week 3 | Open |
| D-03 / Week 1 | Dependency: REQ-06 delivery workflow relies on delivery partners (or an agreed manual process). | Operations Lead | Agree delivery partner and process by Week 4 | Open |
| D-04 / Week 1 | Dependency: D5 pilot launch relies on D4 passing with no critical defects and on 15 sellers / 75 listings being ready. | QA Lead / Operations Lead | Check readiness at the Week 16 milestone review | Open |
| DEC-01 / Week 1 | Decision: initial release is a responsive website, not native apps (per charter), to fit the 16-week timeline. Decided by the project team. | Project Manager | Record in the D1 scope baseline by Week 2 | Closed |
| DEC-02 / Week 1 | Decision: checkout supports cash-on-delivery plus one third-party online payment option (per charter), to keep the MVP simple and limit payment risk. Decided by the project team. | Product Owner / BA | Name the provider once confirmed (see I-01) | Closed |

# 10. Resource and budget management

The draft cash budget is EGP 15,840, including a 10% contingency, and most of the work is covered by non-cash resources such as team time and free tools. Amounts are estimates dated 16 October 2026, in Egyptian pounds (EGP); they must be checked against real quotes once the Sponsor confirms the budget and launch area (issue I-01, due Week 2).

## Cash resources

| Resource / cost item | Quantity | Estimated cost (EGP) | Actual cost (EGP) | Source / owner |
| --- | --- | --- | --- | --- |
| Domain name (1 year) | 1 | 800 |  | Development Lead |
| Web hosting / cloud server for MVP testing and pilot (about 6 months) | 6 months | 3,600 |  | Development Lead |
| Order and reminder messages to sellers and customers (SMS / messaging service, pilot) | 1 pilot allowance | 1,500 |  | Operations Lead |
| Online payment provider: live transaction fees for pilot orders (sandbox access is free) | 1 pilot allowance | 1,000 |  | Payments/Operations Lead |
| Seller onboarding and listing-creation sessions (venue, refreshments, printed guides) | 3 sessions | 4,500 |  | Operations Lead |
| Seller recruitment materials (flyers, social media posts) | 1 set | 2,000 |  | Operations Lead |
| Test deliveries for the delivery workflow (REQ-06) | 20 orders | 1,000 |  | Payments/Operations Lead |
| Contingency (10% of cash items) | 10% | 1,440 |  | Project Sponsor |
| TOTAL |  | 15,840 |  |  |

## Non-cash resources

| Resource | Quantity | Estimated cost | Source / owner |
| --- | --- | --- | --- |
| Project team time for all deliverables D1 to D6 | 24 weeks | In kind | Project Manager |
| Supervisor / Sponsor and Product Owner review time | Every 2 weeks, plus milestone reviews | In kind | Project Sponsor |
| Team members' own laptops, phones and internet for building and testing | Per member | In kind | Each team member |
| Free tools: design (prototype), version control, shared drive, SSL certificate | 1 each | EGP 0 (free tiers) | UX/UI Lead / Development Lead |
| Payment provider sandbox account and access (D-02) | 1 | EGP 0 | Payments/Operations Lead |
| Delivery partner or agreed manual process (D-03) | 1 | To be agreed | Operations Lead |
| Pilot sellers (15) and pilot customers: time for training, orders and feedback | 8 weeks | Volunteer time | Operations Lead |
| Women's groups and local networks for seller recruitment (supports R2) | Several | Volunteer support | Operations Lead |

## Budget rules

- Record the currency (EGP) and the date on which each estimate was obtained; replace draft figures with quotes as they arrive.

- Do not commit to spending or purchasing without Sponsor approval; spending is requested through the change process in section 12.

- Use contingency only with Sponsor approval, and log the reason in the decision log.

- Update the "Actual cost" column every 2 weeks, before the Sponsor update, and explain any item that differs from its estimate by more than 10%.

- If recruitment (R2) or provider problems (R3) need extra spending, the Project Manager raises a change request with the cost impact before any money is spent.

# 11. Change control

After the D1 scope baseline is approved in Week 2, any change to scope, schedule, budget, quality, resources or risk is made only through the process below. It is the main response to risk R1 (scope expansion, score 16) and protects decision DEC-01 (responsive website, not native apps).

| Step | What happens | Owner | Timing |
| --- | --- | --- | --- |
| 1. Log | Requester describes the change and the reason; the Project Manager gives it an ID (CR-01, CR-02 …) | Requester / Project Manager | Within 2 working days |
| 2. Benefit and risk of refusing | State the expected benefit and what happens if the change is rejected | Requester | With the request |
| 3. Assess impact | Estimate effect on tasks, milestone dates (D1 Week 2 to D6 Week 24), budget, quality and risks R1 to R8; include the option "no change" | Product Owner / BA with the affected deliverable owner | Within 5 working days |
| 4. Decide | Approve, reject or defer, using the approval levels below | Approver | Next sponsor update or milestone review; within 24 hours if urgent |
| 5. Update | Plan, schedule, requirements, budget and logs are changed only after approval; team told at the next check-in | Project Manager | Within 2 working days of approval |
| 6. Record and inform | Decision entered in the decision log and sent to everyone affected | Project Manager | Same day as the update |

## Approval levels

| Change type | Approved by |
| --- | --- |
| Inside the approved scope, with no effect on dates or budget (wording, layout, minor fixes) | Product Owner / BA |
| Moves a milestone by one week or less, or affects a Medium or Low priority requirement | Project Manager + Product Owner |
| Adds or removes a High-priority requirement (REQ-01 to REQ-07), moves a milestone by more than one week, changes the budget, or changes the pilot targets | Project Sponsor |

## Rules

- A new idea is not part of the project until its request is approved.

- A change that adds work must show what is removed or which date moves; it cannot simply be added.

- Ideas outside scope are logged as "Deferred" for a future release instead of being lost.

- If a change affects an assumption or dependency, the matching log entry (A-01 to A-02, D-01 to D-04) is updated at the same time.

- After the D3 MVP milestone in Week 14, only defect fixes are accepted before the pilot starts in Week 17.

## Change request log

The first three entries are ideas already named in risk R1 as likely scope growth. They are logged now as proposed deferrals so they can be confirmed with the Sponsor at the Week 2 milestone review.

| Change ID | Requested change / reason | Impact assessment | Decision / approver | Date / plan updated |
| --- | --- | --- | --- | --- |
| CR-01 | Multi-seller cart, so a customer can buy from several sellers in one order. Linked to assumption A-02 (one seller per order is enough for the pilot) | Scope: new cart, payment and delivery logic. Time: likely moves D3 MVP (Week 14). Cost: extra development. Risk: raises R1 and R3 | Defer to a future release (proposed) / Project Sponsor | Week 2 review / D1 baseline |
| CR-02 | Native mobile apps (Android / iOS). Conflicts with DEC-01 | Scope: separate builds and app-store approval. Time: does not fit 16 weeks. Cost: high. Risk: raises R1 and R7 | Defer to a future release (proposed) / Project Sponsor | Week 2 review / D1 baseline |
| CR-03 | Loyalty points for repeat customers | Scope: new feature and rules. Time: adds work after REQ-01 to REQ-07. Risk: raises R1 | Defer to a future release (proposed) / Project Sponsor | Week 2 review / D1 baseline |

# 12. Document and information management

All WHBBM files live in one shared project folder, and only the latest approved version in it counts. The project name used in file names is "WHBBM", short for Women Home-Based Business Marketplace.

| Folder structure | 01_Charter; 02_Planning; 03_Research; 04_Delivery; 05_Testing; 06_Reports; 07_Meetings_and_Logs; 08_Final_Submission. Prototype and MVP files go in 04_Delivery; seller and customer feedback go in 03_Research until the pilot, then 07_Meetings_and_Logs |
| --- | --- |
| File naming | YYYY-MM-DD_WHBBM_DocumentName_vX.X, for example 2026-10-20_WHBBM_RiskRegister_v1.0 |
| Versioning | v0.1 for drafts; v1.0 for the first approved version; v1.1 for minor edits; v2.0 for a major revision. The D1 scope baseline is v1.0 after approval in Week 2 and changes only through change control (section 12) |
| Ownership | Each key file has one named owner, shown in the register below, who updates it and checks accuracy. Each deliverable has a backup owner (risk R7) |
| Access and privacy | Only team members who need a file can open it. Seller and customer personal data (names, phone numbers, addresses, order details) is collected only when needed, kept out of shared or public folders, and handled under the security checklist in D4 (risk R6). Payment card details are never stored by the team; the third-party payment provider handles online payments |
| Backups | Use the approved shared drive; the owner of each file keeps it there, not only on a personal device. The code repository is backed up with the hosting setup |
| Approvals | Record who approved each document, the date and any conditions in the decision log, at the milestone review |
| References | Cite outside facts, images, data and ideas in the required academic referencing style. Disclose any AI tool use when the programme requires it |

## Document register

Versions are drafts until approved at the milestone shown. The storage location is a folder name until the shared drive link is added.

| Document name | Owner | Version | Approval / date | Storage location |
| --- | --- | --- | --- | --- |
| Project charter | Project Manager | v0.1 | Supervisor / Sponsor, before D1 (Week 2) | 01_Charter |
| Project management plan | Project Manager | v0.1 | Supervisor / Sponsor, Week 2 | 02_Planning |
| D1 Scope baseline and requirements (REQ-01 to REQ-08) | Product Owner / BA | v0.1 | Sponsor + Product Owner, Week 2 | 02_Planning |
| Schedule and WBS | Project Manager | v0.1 | Sponsor, Week 2 | 02_Planning |
| Risk, issue, assumption, dependency and decision logs | Project Manager | v0.1 | Reviewed every 2 weeks | 07_Meetings_and_Logs |
| Change request log | Project Manager | v0.1 | Reviewed with each change request | 07_Meetings_and_Logs |
| D2 Prototype and feedback record | UX/UI Lead | v0.1 | Product Owner, Week 5 | 04_Delivery |
| D3 MVP (code and release notes) | Development Lead | v0.1 | Product Owner, Week 14 | 04_Delivery |
| Test log and defect list (D4) | QA Lead | v0.1 | QA Lead + Product Owner, Week 16 | 05_Testing |
| Provider and delivery agreements | Payments/Operations Lead | v0.1 | Sponsor, by Week 4 | 02_Planning |
| Seller recruitment list and pilot feedback and complaint log | Operations Lead | v0.1 | Reviewed weekly in Weeks 17 to 24 | 03_Research / 07_Meetings_and_Logs |
| Budget tracker (section 11) | Project Manager | v0.1 | Sponsor, every 2 weeks | 06_Reports |
| Final report / presentation | Project Manager | v0.1 | Supervisor, Week 24 | 08_Final_Submission |

# 13. Progress monitoring and reporting

The Project Manager sends a status report to the Sponsor and Product Owner every 2 weeks, one working day before the 30-minute sponsor meeting, and the team reviews progress at each check-in. The first report below is provisional and shows how the template is filled from the logs in sections 8 and 9; figures and evidence links are updated before it is sent.

## Status report (first update, Weeks 1–2)

| Reporting period | Weeks 1–2 (first sponsor update, due at the D1 milestone review, Week 2) |
| --- | --- |
| Overall status | Amber (provisional): budget, launch area and service providers are not yet confirmed (I-01), which blocks D1 |
| Completed this period | Management plan sections drafted: communication plan, risk register (R1 to R8), and issue, assumption, dependency and decision logs. Decisions DEC-01 and DEC-02 recorded. Evidence: 02_Planning and 07_Meetings_and_Logs |
| Next period priorities | Confirm budget, launch area and providers with the Sponsor (Project Manager, Week 2). Approve the D1 scope baseline (Product Owner / BA, Week 2). Run the seller and customer survey for A-01 (Product Owner / BA, Week 2). Request payment provider access for D-02 (Payments/Operations Lead, Week 3). Agree the delivery partner or manual process for D-03 (Operations Lead, Week 4). Start seller recruitment through women's groups (Operations Lead) |
| Schedule / budget variance | Schedule: no milestone missed yet; D1 is due Week 2. Budget: draft estimate EGP 15,840 (section 11); actual spending EGP 0 |
| Top risks / issues | I-01 budget, area and providers unconfirmed (open). R1 scope expands, score 16: D1 baseline to be frozen in Week 2. R2 too few sellers or listings, score 15: recruitment started early, checked against 50% of target by Week 12 |
| Decisions / support needed | Project Sponsor: confirm budget, launch area and service providers by Week 2 |

## Status colours

| Colour | Meaning | Examples |
| --- | --- | --- |
| Green | On track | Milestones on date; no line over its estimate by more than 10%; no risk scoring 12 or more without an active response |
| Amber | Needs attention | A milestone may slip by one week or less; any budget line over its estimate by more than 10%; a risk trigger in section 8 has fired and a response is under way |
| Red | Major issue, likely failure | A milestone slips by more than one week; total cost likely above budget plus contingency; a critical defect is open in Weeks 15–16; a Sponsor decision is overdue |

A report that is Amber or Red also states the cause, the recovery options and the decision needed, and is escalated within 24 hours under the urgent escalation rule in section 7.

## Pilot and risk indicators

These measures are checked in each report from the week shown, using the targets and triggers already set in the risk register.

| Measure | Target | Checked from | Warning sign | Owner |
| --- | --- | --- | --- | --- |
| Active sellers | 15 at pilot start | Week 6, then every report | Under 8 sellers by Week 12 (below 50%; R2) | Operations Lead |
| Approved listings | 75 at pilot start | Week 6, then every report | Under 38 listings by Week 12 (below 50%; R2) | Operations Lead |
| Milestone dates | D1 Week 2; D2 Week 5; D3 Week 14; D4 Week 16; D5 and D6 Week 24 | Every report | Late approval of D2 delays D3 (D-01); missed checkpoint (R7) | Project Manager |
| Critical defects | 0 open at go-live | Week 12, then twice weekly in Weeks 12 to 16 | Any critical defect open in Weeks 15 to 16 (R5) | QA Lead |
| Orders fulfilled | 70% or more of seller-accepted orders | Weekly in Weeks 17 to 24 | Below 70% for 2 consecutive weeks (R4) | Operations Lead |
| Customer satisfaction | 4 out of 5 average | Weekly in Weeks 17 to 24 | Average below 4 (R4) | Operations Lead |
| Provider integration dates | As agreed with providers | Every 2 weeks during the build | Provider misses an agreed date (R3) | Payments/Operations Lead |

## Monitoring rules

- The Project Manager compiles each report from the action log, the issue log, the risk register and the budget tracker, and stores it in 06_Reports using the file naming rule in section 13.

- Report facts and evidence links, not general statements.

- Risks are re-scored at every sponsor update; a risk whose trigger has fired moves to the top of the report.

- If a milestone is likely to be missed, the person who sees it first tells the team and the Project Manager at once, with the impact, recovery options and decision needed; they do not wait for the next report.

# 14. Stakeholder and user engagement

| Stakeholder / group | Interest / influence | What they need | Engagement method / timing | Owner |
| --- | --- | --- | --- | --- |
| Women home-based business owners / pilot sellers | High / High | Seller onboarding, product listing support, order management, and clear payment and delivery updates. | Recruit early; interviews in Weeks 1–2; prototype feedback by Week 5; weekly feedback during Weeks 17–24 pilot. | Operations Lead |
| Customers / beneficiaries | High / Medium | Easy product discovery, accurate product information, straightforward checkout, and order-status updates. | Short survey in Weeks 1–2; prototype feedback by Week 5; usability checks before Week 16; pilot feedback weekly. | Product Owner / BA |
| Project Sponsor | High / High | Visibility of scope, budget, launch area, provider choices, risks, progress, and milestone decisions. | Status update every two weeks; confirm budget, launch area, and providers by Week 2; milestone reviews at D1–D6. | Project Manager |
| Product Owner / Business Analyst | High / High | Agreed requirements, prioritised REQ-01 to REQ-07, clear acceptance criteria, and controlled scope. | Requirements workshops in Weeks 1–2; scope baseline approval at D1; prototype review at Week 5; change control throughout. | Project Manager |
| Development and QA team | High / High | Clear priorities, timely decisions, stable requirements, test environments, and defect triage. | Weekly team check-in; twice weekly during Weeks 12–16; milestone reviews and task/action log. | Project Manager |
| Payment provider | Medium / High | Integration requirements, sandbox access, secure payment-status handling, and agreed technical contacts. | Contact during initiation; request sandbox access by Week 3; test before MVP/QA sign-off; retain cash-on-delivery fallback. | Payments / Operations Lead |
| Delivery partners / service providers | High / Medium | Delivery workflow, order details, fee/area coverage, contact points, and escalation process. | Confirm partner or manual process by Week 4; coordination every two weeks during build and weekly during pilot. | Operations Lead |
| Platform administrators | High / Medium | Role-based access, seller/listing moderation, complaint handling, and basic management visibility. | Requirements review in Weeks 1–2; prototype review by Week 5; admin acceptance testing during Weeks 15–16. | Development Lead / Product Owner |

# 15. Ethics, data, and responsible practice

- Obtain informed permission before collecting information from sellers, customers, or other participants during interviews, surveys, onboarding research, and user testing.

- Explain the purpose of collecting feedback and personal information, how it will be used, and who may access it.

- Collect only information needed for seller accounts, product listings, customer orders, payment status, delivery coordination, and support.

- Protect customer contact details and delivery addresses, seller account information, and order records through role-based access and appropriate security controls.

- Share personal or order information with authorised team members and relevant payment/delivery providers only when necessary to fulfil the order.

- Use accurate product descriptions, prices, availability, and genuine or authorised product images. Do not publish misleading claims about products or sellers.

- Apply fair and consistent seller onboarding, listing approval, moderation, and complaint-handling procedures.

- Respect copyright and intellectual property; obtain permission to use product photographs, logos, descriptions, and other third-party materials where required.

- Do not invent seller recruitment numbers, listings, orders, customer feedback, test results, or pilot outcomes. Label assumptions and estimates clearly.

- Confirm and follow applicable privacy, consumer-protection, and payment-security requirements; agree on data retention and deletion practices before launch.

- If AI tools are used, verify outputs, protect confidential information, disclose use when required by the training provider, and keep the team accountable for final work.

- Follow the agreed change-control process and record decisions that affect scope, user data, provider integrations, or pilot readiness.

# 16. Weekly team action tracker

| Week / date | Action | Owner | Due date | Priority | Status / evidence |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Confirm sponsor, budget, launch area, and potential service providers; identify stakeholders and record assumptions/issues. | Project Manager | Week 2 | H | Open / Issue log I-01 |
| Week 2 (D1) | Approve project scope baseline; prioritise REQ-01 to REQ-07; confirm responsive website MVP and change-control process. | Project Manager + Product Owner / BA | Week 2 | H | Pending / Approved D1 baseline |
| Weeks 1–3 | Recruit pilot sellers early and request payment-provider sandbox access; identify delivery partner or manual fallback. | Operations Lead; Payments / Operations Lead | Weeks 3–4 | H | Open / Recruitment and dependency logs |
| Weeks 3–5 (D2) | Validate seller/customer assumptions and review prototype; record feedback and obtain prototype approval before development proceeds. | Product Owner / BA; UX/UI Lead | Week 5 | H | Pending / Prototype approval and feedback log |
| Week 6 | Record the first count of active sellers and approved listings; report the counts in every status report from now on. | Operations Lead | Week 6 | M | Pending / Seller and listing counts |
| Weeks 6–10 | Track development against approved requirements; review scope changes, blockers, and dependencies at weekly check-ins. | Project Manager + Development Lead | Weekly | H | Pending / Task board and action log |
| Weeks 11–14 (D3) | Complete MVP workflows for product listings, orders, payment status, delivery coordination, and administration; verify provider fallback. | Development Lead | Week 14 | H | Pending / MVP review and test evidence |
| Week 12 checkpoint | Check seller recruitment against target; escalate if recruitment is below 50% of the target of 15 active sellers and 75 approved listings at pilot start. | Operations Lead | Week 12 | H | Pending / Seller and listing counts |
| Weeks 15–16 (D4) | Complete QA and user acceptance; verify role-based access and security checklist; do not launch with open critical defects. | QA Lead + Development Lead | Week 16 | H | Pending / QA report and go/no-go decision |
| Weeks 17–24 (D5) | Run the eight-week pilot; monitor fulfilment target of 70% of seller-accepted orders, average satisfaction target of 4/5, feedback, and complaints. | Operations Lead | Weekly through Week 24 | H | Pending / Pilot metrics and feedback log |
| Week 24 (D6) | Review pilot results, document lessons learned, complete handover and support guidance, and record final decisions and outstanding items. | Project Manager + deliverable owners | Week 24 | H | Pending / Evaluation report and handover sign-off |

# 17. Approval and commitment

| Role | Name | Signature / confirmation | Date |
| --- | --- | --- | --- |
| Project Manager / Team Lead | Basant Ahmed | basantnafea@gmail.com | 15 Oct 2026 |
| Team Representative | Nouran Salem | nsass9272@gmail.com | 15 Oct 2026 |
| Supervisor / Assessor | Yassmine El Sharkawy | Pending | Pending |

Confirmations dated 15 October 2026 apply to draft v0.1 of this plan. Signatories re-confirm on the final approved version (v1.0) before submission.